## Sheet1
No | Main Task | SUB - TASK | Description | Assigned | Expected Outpot | Estimated Timeline | TOOLS/TECHNOLOGY
1 | Requirement Analysis |  |  | Business Analyst | Approved FRD (versioned PDF/Doc) | 1–2 weeks | Google Docs, interviews, surveys
1.1 | Functional Requirements |  | Performance, security, usability, availability, privacy requirements.
1.2 |  | Non-Functional Requirements Document | User stories per role (user/admin) based on the required app features.
1.3 |  | User Stories Package | User stories per role (user/admin) based on the required app features.
1.4 |  | Requirements Sign-off Package | Final review notes and sign-off record of requirements baseline.
1.5 |  | Requirements Traceability Matrix (RTM) | Mapping FRD/NFRD → design modules → test cases.
2 | System Design
2.1 |  | UX Research & User Flow Package | Personas, journey maps, and user flows (onboarding, logging, meal plan,
2.2 |  | Wireframes & Interactive Prototype Package | Wireframes + clickable prototype for main screens.
2.3 |  | UI Style Guide Package | Color palette, typography, components, spacing, icons.
2.4 |  | System Architecture Design Package | Architecture diagram (mobile app + Firebase backend + integrations), securityapproach.
2.5 |  | Database Design Package (ERD + Data Dictionary) | ERD for users, goals, workouts, meals, logs, nutrients, notifications.
2.6 |  | Firebase Data Model & Security Rules Specification Package | Defines Firestore collections/documents structure, Firebase Authentication flow, and Firestore Security Rules for data access.
3 | Development
3.1 |  | Mobile Application (Frontend) | React Native Android UI modules: auth, profile/goals, tracking, meals, macros, dashboard, notifications, settings.
3.1.1 |  | Authentication & Onboarding Module | Login/register, onboarding steps, consent/privacy prompts.
3.1.2 |  | User Profile & Goals Module | Profile edit, goal setup (weight, calorie, steps), preferences
3.1.3 |  | Fitness Tracking Module (Manual Logging + Summaries) | Manual activity logging (steps/time/calories) and daily summary view.
3.1.4 |  | Workout Plan Module | Workout plan list, workout details, completion logging.
3.1.5 |  | Meal Planning Module | Meal plan builder (breakfast/lunch/dinner/snacks), schedule.
3.1.6 |  | Nutrition & Macro Tracking Module | Food search/add, macros summary (calories, protein, carbs, fats)
3.1.7 |  | Progress Dashboard & Analytics Module | Charts for weight trend, calories, workouts, adherence.
3.1.8 |  | Notifications & Reminders Module | Reminders for meals/workouts/water (as defined), notification preferences.
3.1.9 |  | Settings & Preferences Module | Units (kg/lb), privacy settings, data export request (if required), logout.
3.2 | Firebase Backend Services
3.2.1 |  | Authentication & Authorization Configuration | Configure user sign-up/sign-in and access control using Firebase Authentication.
3.2.2 |  | User Profile & Goals Data Service | Set up Firestore data structure for user profiles, goals, and preferences.
3.2.3 |  | Fitness Tracking Data Service | Store and retrieve activity logs and workout completion records in Firestore.
3.2.4 |  | Workout Plan Data Service | Store workout plans/templates and user workout schedules in Firestore.
3.2.5 |  | Meal Planning & Nutrition Data Service | Store meal plans, food logs, and nutrition/macro entries in Firestore.
3.2.6 |  | Analytics/Progress Queries Package | Create queries needed for dashboard summaries (daily/weekly progress).
3.2.7 |  | Push Notifications Configuration | Configure push notifications for reminders and updates.
3.2.8 |  | Security Rules & Error Logging Setup | Configure Firestore Security Rules and basic app error logging.
3.3 | Cloud Firestore Database Implementation
3.3.1 |  | Firestore Collections & Document Structure Package | Implement the final Firestore collections/documents based on the database design.
3.3.2 |  | Seed/Reference Data Package | Add initial/reference data (units, categories, default lists if needed).
3.3.3 |  | Backup & Restore Package | Create backup/export procedure and restore steps for Firestore data.
3.4 | Integrations |  | Connect external services (Google Fit, USDA API, and FCM notifications).
3.4.1 |  | Wearable/Health Data Integration (Google Fit) | Read health metrics (steps, calories, workouts) based on permissions.
3.4.2 |  | Nutrition/Food Data API Integration (USDA FoodData Central) | Food search and nutrition facts via third-party API.
3.4.3 |  | Push Notifications Integration (FCM) | Device token registration and push delivery setup.
4 | Testing
4.1 |  | Test Plan Package | Testing scope, strategy, test types, entry/exit criteria.
4.2 |  | Unit Test Suite | Unit tests for core app logic and utilities.
4.3 |  | Integration Test Suite | Integration tests for Firebase Authentication/Firestore operations and data
4.4 |  | System & End-to-End Test Report | End-to-end testing of user flows (log workout, plan meals, dashboard).
4.5 |  | Usability Test Report | Usability feedback from test users; improvements list.
4.6 |  | Security Test Report | Basic security checks (Firebase Authentication, Firestore Security Rules, data
4.7 |  | Performance Test Report | App responsiveness and Firestore query performance checks.
4.8 |  | UAT Sign-off Package | User acceptance testing scripts and sign-off.
4.9 |  | Defect Closure Report | Defect summary, fixed/deferred list, final quality status
5 | Deployment
5.1 |  | Environment Setup Package (Dev/Test/Prod) | Hosting, database, secrets/config, access controls
5.2 |  | CI/CD Pipeline Package | Automated build/test/deploy pipeline.
5.3 |  | Release Package (APK/AAB + release notes) | Release-ready binaries and notes.
5.4 |  | Production Deployment & Smoke Test Package | Go-live deployment and verification checklist.
5.5 |  | Rollback/Hotfix Package | Rollback plan and quick hotfix procedure.
6 | Documentation
6.1 |  | User Manual Package | Guide for users (setup goals, log workouts, meal plan, view progress).
6.2 |  | Admin/Operations Guide Package | Admin/ops procedures (monitoring, troubleshooting, configs).
6.3 |  | Technical Documentation Package (Architecture/Firebase/Database) | As-built technical documentation for maintenance.
6.4 |  | Training & Demo Materials Package | Slides, demo script, and sample scenarios for presentation.